## Gantt
	predicted time(hrs)	time spent(hrs)		08/26/19					10/14/19					12/09/19				01/06/20					02/24/20					05/01/20
Nikolai			weeks	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45
research and purchase dev board	5	5
test range	10	6
design and develop mesh network	30	3
implement security	10
testing	15	2
peer review	10
documentation	10	15
totals	90	16
Tyrel
research simulation products	10
determine needed data	2
design transmission payload	5
design and implement database	5
design simulation environment	15
implement data into simulation	10
testing	15
peer review	10
documentation	10
totals	82	0
Zane
research and purchase sensor options	5
test sensor options	10
calculate power usage	5
research and purchase power solution	2
design and build case	20
installation	2
testing	15
peer review	10
documentation	10
totals	79	0
group totals (hrs)	251	16
group totals ($)	$25,100.00	$1,600.00

	planned
	current
	completed
	late

## Gantt_2
	08/26/19					10/14/19					12/09/19				01/06/20					02/24/20					05/01/20
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36
Documentation
Research and purchase products
Test LoRa range
Determine needed data
Test sensors
Calculate power usage, research and purchase power solution
Design and develop mesh network, simulation environment, and units
Installation
Testing
Prepare for expo

## Management_Summary
	Total				Coding				Meetings				Systems Analysis
	Budgeted	Actual	Deficit		Budgeted	Actual	Deficit		Budgeted	Actual	Deficit		Budgeted	Actual	Deficit
Nikolai	$11,700.00	$2,600.00	$9,100.00		$9,000.00	$1,600.00	$7,400.00		$1,000.00	$1,000.00	$0.00		$1,700.00	$0.00	$1,700.00
Tyrel	$10,800.00	$900.00	$9,900.00		$8,200.00	$0.00	$8,200.00		$1,000.00	$900.00	$100.00		$1,600.00	$0.00	$1,600.00
Zane	$10,500.00	$1,000.00	$9,500.00		$7,900.00	$0.00	$7,900.00		$1,000.00	$1,000.00	$0.00		$1,600.00	$0.00	$1,600.00
Total	$33,000.00	$4,500.00	$28,500.00		$25,100.00	$1,600.00	$23,500.00		$3,000.00	$2,900.00	$100.00		$4,900.00	$0.00	$4,900.00

## Meetings
	Date	Aug 29	Sep 05	Sep 12	Sep 19	Oct 03	Oct 10	Oct 17	Oct 24	Nov 05	Nov 12	Nov 21	Nov 28	Dec 05	Dec 12
	Purpose	Team Meeting	First Customer Meeting	Team Meeting	Second Customer Meeting	Team Meeting	Team Meeting	Team Meeting	Teem Meeting	PDR	Team Meeting
	Hours	1	1	1	1	1	1	1	1	1	1	1	1	1	1
Nikolai	10	ü	ü	ü	ü	ü	ü	ü	ü	ü	ü
Tyrel	9	ü	ü	ü	ü	ü	ü	ü	ü		ü
Zane	10	ü	ü	ü	ü	ü	ü	ü	ü	ü	ü
Total	29	3	3	3	3	3	3	3	3	2	3	0	0	0	0

ü

## SA
	Task	Predicted(hrs)	spent(hrs)	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15
Nikolai	Technical Specs	5	6
	Meeting Notes	5	6
	SRS	5	6
	SRS2	2	1
	PDR - LoRa Portion		2
	CDR - Battery, LoRa Milestones		1
	Subtotal	17	22
Tyrel	Gantt	5
	Budget	5
	PDR	3
	PDR2	1
	CDR2	1
	Updated Budget and Gantt	1

	Subtotal	16	0
Zane	Diagrams	4
	Contract	2
	Project Plan	4
	PDR Diagrams	2
	Concept Art	3
	Updated Project Plan	1

	Subtotal	16	0
	Total	49	22

## Budget
Item	Description	QTY	Est Price	Est Totals	*Blue Font indicates an estimated price due to additional research needed on that product. / -Figuring 7 sets of sensors.
Boards	Arduino Pro Mini 328	10	9.45	$94.50
LORA	Adafruit RFM95W LoRa Radio Transceiver	10	17.96	$179.60
Headers	Female and Male Header Bundle	1	30	$30.00
Antenna	900 Mhz Antenna Kit for LoRa w/connector	10	13.5	$135.00
3D Printing Materials	White 3D printer filament	3	19.99	$59.97
Batteries	TBD	7	20	$140.00
Sensors	TBD	7	20	$140.00
Den Receiver	TBD	1	100	$100.00
Adhesive/ Mounting	TBD	5	10	$50.00
Paint	TBD	3	5	$15.00

			Subtotal	$944.07
			Goal	$1,500.00
			Difference	$555.93

Item	Actual Description	QTY	Actual Price	Actual Totals
Boards	Arduino MKR 1310	2	42	$84.00
LORA	Adafruit RFM95W LoRa Radio Transceiver	3	19	$57.00
Headers				$0.00
Antenna	900 Mhz Antenna Kit for LoRa w/connector	2	10.99	$21.98
3D Printing Materials	White 3D printer filament			$0.00
Batteries	TBD			$0.00
Sensors	TBD			$0.00
Den Receiver	TBD			$0.00
Adhesive/ Mounting	TBD			$0.00
Paint	TBD

			Subtotal	$162.98
			Goal	$1,500.00
			Difference	$1,337.02